## DMR
[5 empty] | WBM Daily Drilling Fluids Report | [22 empty] | 1
[9 empty] | Project ID | [10 empty] | Report Date |  |  | 11/26/2025 | [6 empty] | Report No. |  |  |  | 1
Well Name | SA-1284 | [7 empty] | Rig Name |  |  |  |  | SP-284 | [5 empty] | Field/Block |  |  | SABRIYAH | [6 empty] | Location/State |  |  |  | Kuwait
Operator | Kuwait Oil Company | [7 empty] | Contractor |  |  |  |  | Sinopec | [5 empty] | Formation |  |  | KUWAIT SERIES | [6 empty] | MD (ft) |  |  |  | 96.0
Operator Rep | Kamta Tiwari / Mohamed Nagib | [7 empty] | Contractor Rep |  |  |  |  | Lee | [5 empty] | Inclination/Azimuth (°) |  |  | 0.00/0.00 | [6 empty] | TVD (ft) |  |  |  | 96.0
Spud Date | 11/26/2025 | [7 empty] | Fluid Name |  |  |  |  | GEL MUD | [5 empty] | Activity |  |  | Testing | [6 empty] | Bit Depth (ft) |  |  |  | 96.0
Drill String | [18 empty] | Casing / Open Hole | [10 empty] | Bit Information
Type | [6 empty] | OD (in) |  |  |  | ID (in) |  |  |  | Length (ft) |  |  |  | Type |  |  | OD (in) |  |  | Shoe MD (ft) |  |  |  |  | Bit Type |  |  |  | MT-TCI
8.25" NMDC | [6 empty] | 8.250 |  |  |  | 2.810 |  |  |  | 6.8 |  |  |  | 30" CSG |  |  | 30.000 |  |  | 65.0 |  |  |  |  | Bit Model |  |  |  | VAREL
Stabiliser | [6 empty] | 8.250 |  |  |  | 3.000 |  |  |  | 8.6 |  |  |  | 22" OPEN HOLE |  |  | 22.000 |  |  | 96.0 |  |  |  |  | Bit Size (in) |  |  |  | 22.000
MWD sub | [6 empty] | 9.250 |  |  |  | 2.810 |  |  |  | 1.6 | [14 empty] | Nozzles
Telescope | [6 empty] | 9.120 |  |  |  | 5.110 |  |  |  | 25.2 | [14 empty] | Number |  |  |  | Size
MWD sub | [6 empty] | 8.250 |  |  |  | 2.810 |  |  |  | 1.1 | [14 empty] | 4 |  |  |  | 20
Pony NMDC | [6 empty] | 8.250 |  |  |  | 2.810 |  |  |  | 13.2
Stabiliser | [6 empty] | 8.250 |  |  |  | 3.000 |  |  |  | 7.0
Motor | [6 empty] | 9.630 |  |  |  | 7.850 |  |  |  | 32.6 | [14 empty] | TFA (in2) |  |  |  | 1.227
Active Volume Balance (bbl) | [18 empty] | Volume Summary (bbl) |  |  |  |  | Vol (bbl) |  |  | Active Pit Description | [8 empty] | Vol (bbl)
|  |  |  | Daily |  | Cum. Int. | [7 empty] | Daily |  |  |  | Cum. Int. | Active Pit Vol |  |  |  |  | 323.76 |  |  | Sand trap | [8 empty] | 130.00
Starting Volume |  |  |  | 0.00 |  |  |  |  | Shakers/Hydroclones |  |  |  |  | 15.00 |  |  |  | 15.00 | Annular Volume |  |  |  |  | 58.34 |  |  | Desander 1A
Received from Reserve/Other | [5 empty] | 0.00 |  |  | Cuttings Retention |  |  |  |  | 0.00 |  |  |  | 0.00 | Drillstring Volume |  |  |  |  | 2.90 |  |  | Desilter 1B
Product Addition |  |  |  | 32.29 |  | 32.29 |  |  | Centrifuge |  |  |  |  | 0.00 |  |  |  | 0.00 | Downhole Vol |  |  |  |  | 61.24 |  |  | Intermidiate 2A | [8 empty] | 98.00
Weight Material Addition |  |  |  | 56.42 |  | 56.42 |  |  | Evaporation |  |  |  |  | 0.00 |  |  |  | 0.00 | Total Circ. Vol |  |  |  |  | 385.00 |  |  | Intermediate 2B | [8 empty] | 95.76
Base Oil Addition | [5 empty] | 0.00 |  |  | Dumped |  |  |  |  | 0.00 |  |  |  | 0.00 | Vol Below Bit |  |  |  |  | 0.00 |  |  | Intermedate 2 C
Water Addition |  |  |  | 1411.29 |  | 1411.29 |  |  | Formation |  |  |  |  | 0.00 |  |  |  | 0.00 | Reserve Vol |  |  |  |  | 1100.00 |  |  | Trip Tank
Whole Fluid Addition | [5 empty] | 0.00 |  |  | Pit Cleaning |  |  |  |  | 0.00 |  |  |  | 0.00 | Daily Vol Built (Active/Reserve) |  |  |  |  | 1500.00/0.00
Total Additions |  |  |  | 1500.00 |  | 1500.00 |  |  | Tripping |  |  |  |  | 0.00 |  |  |  | 0.00 | Daily Vol Lost (Active/Reserve) |  |  |  |  | 15.00/0.00
Transfer to Reserve/Other |  |  |  | 1100.00 |  | 1100.00 |  |  | Others |  |  |  |  | 0.00 |  |  |  | 0.00 | Daily Vol Returned (Active/Reserve) |  |  |  |  | 0.00/0.00
Return to Warehouse/Rig/Other |  |  |  | 0.00 |  | 0.00 |  |  | Total Losses |  |  |  |  | 15.00 |  |  |  | 15.00 | Volume Not Fluid
Total Transfers Out |  |  |  | 1100.00 |  | 1100.00 |  |  | Final Active Volume |  |  |  |  | 385.00 |  |  |  |  | Total Fluid Volume at Rigsite |  |  |  |  | 1485.00
Fluid Property | [5 empty] | Primary |  |  |  | #2 |  |  | #3 |  |  |  | Plan |  | Product Usage
Description | [5 empty] | THICK GEL MUD |  |  |  | GEL MUD | [6 empty] | GEL MUD |  | Product Name |  |  |  | Size |  | Used |  |  |  | Cum. Used |  |  | Unit Cost (Kwd) |  |  |  | Daily Cost (Kwd)
Sample from | [5 empty] | Flow Line |  |  |  | Reserve | [8 empty] | BARITE 4.1 - BIG BAG |  |  |  | 1.50 Ton |  | 27.00 |  |  |  | 27.00 |  |  | 90.000 |  |  |  | 2430.000
Time Sample Taken |  |  | (hh:mm) |  |  | 23:30 |  |  |  | 18:00 | [8 empty] | BENTONITE - TON |  |  |  | 1.00 Ton |  | 14.00 |  |  |  | 14.00 |  |  | 42.000 |  |  |  | 588.000
Flowline T. |  |  | (°F) |  |  | 80.0 | [12 empty] | CAUSTIC SODA |  |  |  | 25.00 kg |  | 10.00 |  |  |  | 10.00 |  |  | 5.920 |  |  |  | 59.200
Depth |  |  | (ft) |  |  | 75.0 | [12 empty] | SODA ASH |  |  |  | 25.00 kg |  | 13.00 |  |  |  | 13.00 |  |  | 4.500 |  |  |  | 58.500
*MW |  |  | (ppg) |  |  | 9.50 |  |  |  | 9.50 | [6 empty] | 9.50 - 9.60
Funnel Visc. |  |  | (sec/qt) |  |  | 57.0 |  |  |  | 40.0 | [6 empty] | 45.0 - 65.0
T. for PV |  |  | (°F) |  |  | 120.0 |  |  |  | 120.0
*PV |  |  | (cP) |  |  | 10.0 |  |  |  | 8.0
*YP |  |  | (lbf/100ft2) |  |  | 26.0 |  |  |  | 18.0 | [6 empty] | 20.0 - 25.0
R600/R300 | [5 empty] | 46/36 |  |  |  | 34/26
R200/R100 | [5 empty] | 31/23 |  |  |  | 21/18
R6/R3 | [5 empty] | 16/14 |  |  |  | 11/10
Gel 10 sec/10 min/30 min | [5 empty] | 15.0/23.0/25.0 |  |  |  | 10.0/15.0/18.0 | [6 empty] | 6.0/8.0/ - 15.0/25.0/
API Filtrate |  |  | (mL/30min)
API Cake Thickness |  |  | (1/32in)
T. for HTHP |  |  | (°F) | [15 empty] | Recommended Treatment
HTHP Filtrate |  |  | (mL/30min) | [15 empty] | * Checked properties of water well 793/794: Salinity: 2500 / 2600 ppm and Hardness as Ca2+ 580 / 600 ppm. - Checked and function tested Mud system, observed no leakage, - Function tested shale shaker and hoppers. Dressed all 3 shale shakers with API 80 screens. Calibrated Mud Balance. - Received Chemicals from UOP LMP as per inventory. - Built 1500 bbl of 9.5 ppg Gel Mud using 0.36 ppb CAUSTIC SODA for pH, 0.47 ppb SODA ASH to treat out Calcium ion, 17.6 ppb BENTONITE as gelling agent and 59.4 ppb BARITE as weighed material. - Transferred 400 bbl of Gel Mud to Active Pit & mixed Thick Gel Mud to Spud the well using 11 ppb BENTONITE. (FV 57sec & MBT 22.5ppb). - Mud Property: 1st column shown Thick Gel Mud readings and 2nd column shown Normal Gel Mud readings. - Note: The Mud Engineering Services started from 24-November-2025. (03 Days). * KOC deisel stock 166 bbls. * Formation: Kuwait Series. Lithology: Sand * Formation Tops: : * Cumulative cost for 22" Hole: KD 3135.700
HTHP Cake Thickness |  |  | (1/32in)
Solids |  |  | (%) |  |  | 6.0 |  |  |  | 6.0
*Oil |  |  | (%)
*Water |  |  | (%) |  |  | 94.0 |  |  |  | 94.0
Sand Content |  |  | (%)
MBT Capacity |  |  | (lb/bbl) |  |  | 22.50 |  |  |  | 17.50 | [6 empty] | 10.00 - 20.00
pH | [5 empty] | 10.00 |  |  |  | 10.00 | [6 empty] | 9.50 - 10.50
Mud Alkalinity |  |  | (Pm) (mL) |  |  | 1.00 |  |  |  | 1.00
Filtrate Alkalinity |  |  | (Pf) (mL) |  |  | 0.40 |  |  |  | 0.40
Filtrate Alkalinity |  |  | (Mf) (mL) |  |  | 0.50 |  |  |  | 0.50
Calcium |  |  | (mg/L) |  |  | 200 |  |  |  | 200 | [6 empty] | - 400
*Chlorides |  |  | (mg/L) |  |  | 2600 |  |  |  | 2600
Total Hardness |  |  | (mg/L)
Excess Lime |  |  | (lb/bbl) |  |  | 0.16 |  |  |  | 0.16
K+ |  |  | (mg/L)
Make up Water: Chlorides |  |  | (mg/L) |  |  | 2600 |  |  |  | 2600
Solids Adjusted for Salt |  |  | (%) |  |  | 5.9 |  |  |  | 5.9
Fine LCM |  |  | (lb/bbl)
Solids Analysis | [18 empty] | Operational Comments
Brine Density |  |  | SG |  |  | 1.00 |  |  |  | 1.00 | [8 empty] | * Rig move to SA-1284 100%, Rig up: 100%. N/up 29-1/2'' diverter & function test. - P/up & M/up 5" DP, HWDP, 8 1/4" DC Stands and rackback on Derrick. - P/up, M/up & RIH 22" TCI Bit with SLB Motor BHA & tagged bottom at 65 ft. - Rig spud in Well SA-1258 on 26-November-2025 at 23:30 Hr. * Started drilling 22" Vertical hole from 65 ft to 96 ft with 100% returns at report time. - Drilling parameter (Q:300 GPM, WOB: 05/10 klb, Tq:1.5-2.5 Kft/lb, RPM:40,SPP: 90-140 psi). * Forecast operation for the next 24 hrs: Drill 22" Vertical Hole to Section TD at 1228 ft. Circulate hole clean, POOH & L/dn BHA, Rig/up & lower 18 5/8" Csg. RIH Stinger assembly and perform cement job. * Planned total depth for 22" hole is 1228 ft. * Planned total depth for SA-1284 is 9590 ft. * Well Objective: To Drill Mauddud G Single Producer Horizontal Well in Sabriyah field. * Well Profile: SA-MA-SP-H-SSD-PKR
Diss. Solids |  |  | % |  |  | 0.1 |  |  |  | 0.1
Corr. Solids |  |  | % |  |  | 5.9 |  |  |  | 5.9
Low Gravity Solids |  |  | % |  |  | 3.2 |  |  |  | 3.2
Low Gravity Solids |  |  | lb/bbl |  |  | 29.27 |  |  |  | 29.27
High Gravity Solids |  |  | % |  |  | 2.7 |  |  |  | 2.7
High Gravity Solids |  |  | lb/bbl |  |  | 39.44 |  |  |  | 39.44
Average SG Solids |  |  | SG |  |  | 3.33 |  |  |  | 3.33
0
Rheology/Hydraulics
Type |  | 28.500 x 8.250 x 2.810 | 28.500 x 8.250 x 3.000 |  |  | 28.500 x 9.250 x 2.810 |  |  |  | 28.500 x 9.120 x 5.110 |  |  | 28.500 x 8.250 x 2.810 |  |  |  | 28.500 x 8.250 x 3.000
Length (ft) |  | 6.8 | 8.6 |  |  | 1.6 |  |  |  | 25.2 |  |  | 14.3 |  |  |  | 7.0
Ann. Vel. (ft/min) |  | 9.9 | 9.9 |  |  | 10.1 |  |  |  | 10.1 |  |  | 9.9 |  |  |  | 9.9
Crit. Vel (ft/min) |  | 219.8 | 219.8 |  |  | 216.9 |  |  |  | 217.2 |  |  | 219.8 |  |  |  | 219.8
DS Vel (ft/min) |  | 15.5 | 13.6 |  |  | 15.5 |  |  |  | 4.7 |  |  | 15.5 |  |  |  | 13.6
DS P. Loss (psi) |  | 1 | 2 |  |  | 3 |  |  |  | 3 |  |  | 6 |  |  |  | 7
Ann. P. Loss (psi) |  | 0 | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  |  | 0
Pressure Losses | [7 empty] | ECD/ESD | [10 empty] | Drilling Parameters
Total P. Loss (psi) |  |  | 60 |  |  |  |  | ECD /+ Cut at Shoe (ppg) | [6 empty] | 9.63 |  |  |  | Rotary (rpm) |  |  |  | 40.0 |  |  | Pick Up Weight (lbf)
Bit Loss (psi/%) |  |  | 52/87.7 |  |  |  |  | ECD /+ Cut at TD (ppg) | [6 empty] | 9.65 |  |  |  | ROP (ft/hr) | [6 empty] | Slack Off Weight (lbf)
DS Loss (psi/%) |  |  | 7/11.0 |  |  |  |  | ESD /+ Cut at Shoe (ppg) | [6 empty] | 9.50 |  |  |  | Weight on Bit (lbf) |  |  |  | 5 |  |  | On-Bottom Rotate Weight (ft-lb) | [8 empty] | 2500
Ann. Loss (psi/%) |  |  | 1/1.3 |  |  |  |  | ESD /+ Cut at TD (ppg) | [6 empty] | 9.50 |  |  |  | BHCT (°F) | [6 empty] | Off-Bottom Rotate Weight (ft-lb) | [8 empty] | 1500
DH Tools P. Loss (psi/%) |  |  | 0/0.0 |  |  |  |  | Bit Data/Fluid Properties | [10 empty] | Circulation Info | [5 empty] | Solids Control Equipment
Motor P. Loss (psi/%) |  |  | 0/0.0 |  |  |  |  | Bit JV (ft/s) | [6 empty] | 78 |  |  |  | Pump Pressure (psi) |  | 140 |  |  |  | Type | [5 empty] | Info/API Number | [5 empty] | Hours
[8 empty] | Bit HHP (HP)/HSI | [6 empty] | 9.1/0.02 |  |  |  | Flow Rate (gpm) |  | 299.9 |  |  |  | Shaker | [5 empty] | 80/80/80/80 | [5 empty] | 1.00
[8 empty] | PV/YP | [6 empty] | 10.0/26.0 | [5 empty] | Strokes |  | Minutes |  | Shaker | [5 empty] | 80/80/80/80 | [5 empty] | 1.00
Pump Data | [18 empty] | Surf. - Bit |  | 25 |  | 0 |  | Shaker | [5 empty] | 80/80/80/80 | [5 empty] | 1.00
|  |  | 1 |  |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  | Btm up |  | 498 |  | 8
Liner ID (in) |  |  | 6.500 |  |  |  |  | 6.500 | [10 empty] | Surf. - Surf. |  | 523 |  | 9
Stroke Length (ft) |  |  | 12.000 |  |  |  |  | 12.000 | [10 empty] | Pits |  | 2766 |  | 45
Efficiency (%) |  |  | 95.0 |  |  |  |  | 95.0 | [10 empty] | Cuttings Analysis
Stroke/Min |  |  | 61 | [15 empty] | Depth Drilled Last 24 hrs (ft) |  |  |  | 96.0 | [7 empty] | In (ppg) |  | Out (ppg) |  |  |  | Hours
bbl/Stroke |  |  | 0.1170 |  |  |  |  | 0.1170 | [10 empty] | Vol. Drilled Last 24 hrs (bbl) |  |  |  | 45.14 |  | Degasser
Cost Summary | [15 empty] | Fluid Engineer (s) | [8 empty] | Desander
Cost Category | [5 empty] | Kwd | [9 empty] | Ebrahim Shaikh | [8 empty] | Desilter
Daily Product Cost | [5 empty] | 3135.700 | [9 empty] | 95516706 | [8 empty] | Centrifuge
Section Product Cost | [5 empty] | 3135.700 | [9 empty] | ebrahim.shaikh@uqdfkt.com
Daily Eng. Cost | [5 empty] | 520.002
Section Eng. Cost | [5 empty] | 520.002
Cum. Product Cost | [5 empty] | 3135.700
Cum. Eng. Cost | [5 empty] | 520.002
Total Daily Cost | [5 empty] | 3655.702
Total Well Cost | [5 empty] | 3655.702
This report and the information contained therein is provided without any guarantee or warranty of any kind, either express or implied, including, but not limited to, warranties of merchantability, fitness for a particular purpose, of title, or of infringement of third party rights. Use of the information provided in this report is at the user’s risk.

## Inventory
|  |  |  | Daily Inventory Report | [9 empty] | 1
|  |  |  | Project ID | [6 empty] | Report Date |  | 11/26/2025 |  |  |  |  | Report No. |  | 1
Well Name | SA-1284 |  |  | Rig Name |  |  | SP-284 |  |  |  | Field/Block |  | SABRIYAH |  |  |  |  | Location/State |  | Kuwait
Operator | Kuwait Oil Company |  |  | Contractor |  |  | Sinopec |  |  |  | Formation |  | KUWAIT SERIES |  |  |  |  | MD (ft) |  | 96.0
Operator Rep: | Kamta Tiwari / Mohamed Nagib |  |  | Contractor Rep |  |  | Lee |  |  |  | Inclination/Azimuth (°) |  | 0.00/0.00 |  |  |  |  | TVD (ft) |  | 96.0
Spud Date | 11/26/2025 |  |  | Fluid Name |  |  | GEL MUD |  |  |  | Activity |  | Testing |  |  |  |  | Bit Depth (ft): |  | 96.0
Products Inventory | [19 empty] | Concentration (lb/bbl)
Product Name |  | Size |  | Price (Kwd) |  | Start Qty |  | Recived | Cum. Rec. |  | Returned | Cum. Ret. | Used |  | Cum. Used |  | Final |  | Cost (Kwd) | Starting |  | Ending
BARITE 4.1 - BIG BAG |  | 1.50 Ton |  | 90.000 |  |  |  | 40.00 | 40.00 |  |  | 0.00 | 27.00 |  | 27.00 |  | 13.00 |  | 2430.000 |  |  | 54.00
BENTONITE - TON |  | 1.00 Ton |  | 42.000 |  |  |  | 28.00 | 28.00 |  |  | 0.00 | 14.00 |  | 14.00 |  | 14.00 |  | 588.000 |  |  | 18.67
CAUSTIC SODA |  | 25.00 kg |  | 5.920 |  |  |  | 148.00 | 148.00 |  |  | 0.00 | 10.00 |  | 10.00 |  | 138.00 |  | 59.200 |  |  | 0.37
SODA ASH |  | 25.00 kg |  | 4.500 |  |  |  | 160.00 | 160.00 |  |  | 0.00 | 13.00 |  | 13.00 |  | 147.00 |  | 58.500 |  |  | 0.48
MICA COARSE |  | 25.00 kg |  | 3.500 |  |  |  | 48.00 | 48.00 |  |  | 0.00 | 0 |  | 0.00 |  | 48.00
MICA FINE |  | 25.00 kg |  | 3.500 |  |  |  | 48.00 | 48.00 |  |  | 0.00 | 0 |  | 0.00 |  | 48.00
MICA MEDIUM |  | 25.00 kg |  | 3.500 |  |  |  | 112.00 | 112.00 |  |  | 0.00 | 0 |  | 0.00 |  | 112.00
NUTSHELLS COARSE |  | 25.00 kg |  | 4.000 |  |  |  | 56.00 | 56.00 |  |  | 0.00 | 0 |  | 0.00 |  | 56.00
NUTSHELLS FINE |  | 25.00 kg |  | 4.000 |  |  |  | 56.00 | 56.00 |  |  | 0.00 | 0 |  | 0.00 |  | 56.00
QDEFOAM S |  | 55.00 gal |  | 140.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
QPAC LV |  | 25.00 kg |  | 28.280 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
QSCAV H2S |  | 55.00 gal |  | 175.000 |  |  |  | 4.00 | 4.00 |  |  | 0.00 | 0 |  | 0.00 |  | 4.00
QSTAR MT |  | 25.00 kg |  | 9.320 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
QXAN |  | 25.00 kg |  | 46.000 |  |  |  | 120.00 | 120.00 |  |  | 0.00 | 0 |  | 0.00 |  | 120.00
ZINC CARBONATE |  | 25.00 kg |  | 25.000 |  |  |  | 29.00 | 29.00 |  |  | 0.00 | 0 |  | 0.00 |  | 29.00
MAXRELEASE W |  | 55.00 gal |  | 135.250 |  |  |  | 8.00 | 8.00 |  |  | 0.00 | 0 |  | 0.00 |  | 8.00
LIME |  | 25.00 kg |  | 2.100 |  |  |  | 80.00 | 80.00 |  |  | 0.00 | 0 |  | 0.00 |  | 80.00
GS SEAL |  | 25.00 kg |  | 15.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
MAXCLAY |  | 25.00 kg |  | 19.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
MAXLIG |  | 50.00 lb |  | 21.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
QMUL I EH |  | 55.00 gal |  | 184.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
QMUL II EH |  | 55.00 gal |  | 170.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
SIZED CALCIUM CARBONATE COARSE |  | 1.00 Ton |  | 105.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
SIZED CALCIUM CARBONATE MEDIUM |  | 1.00 Ton |  | 105.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
SODIUM BICARBONATE |  | 25.00 kg |  | 6.000 |  |  |  | 56.00 | 56.00 |  |  | 0.00 | 0 |  | 0.00 |  | 56.00
MAXWET XL |  | 55.00 gal |  | 142.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
SIZED CALCIUM CARBONATE FINE |  | 1.00 Ton |  | 105.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
STRATALUBE |  | 55.00 gal |  | 260.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
Chrome Free Ligno Sulphonate |  | 50.00 lb |  | 10.000 |  |  |  | 33.00 | 33.00 |  |  | 0.00 | 0 |  | 0.00 |  | 33.00
DRILLING DETERGENT |  | 55.00 gal |  | 75.000 |  |  |  | 4.00 | 4.00 |  |  | 0.00 | 0 |  | 0.00 |  | 4.00
QMAXCOAT |  | 55.00 gal |  | 103.990 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
WELLKLEEN |  | 55.00 gal |  | 355.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
LCM MIX COARSE |  | 25.00 kg |  | 7.450 |  |  |  | 104.00 | 104.00 |  |  | 0.00 | 0 |  | 0.00 |  | 104.00
LCM MIX FINE |  | 25.00 kg |  | 7.450 |  |  |  | 100.00 | 100.00 |  |  | 0.00 | 0 |  | 0.00 |  | 100.00
LCM MIX MEDIUM |  | 25.00 kg |  | 7.450 |  |  |  | 90.00 | 90.00 |  |  | 0.00 | 0 |  | 0.00 |  | 90.00
Cotton Seeds Hull |  | 25.00 kg |  | 7.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
NUTSHELLS MEDIUM |  | 25.00 kg |  | 4.000 |  |  |  | 53.00 | 53.00 |  |  | 0.00 | 0 |  | 0.00 |  | 53.00
QSTAR HT |  | 25.00 kg |  | 12.350 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
QXAN PREMIUM |  | 25.00 kg |  | 75.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
QMAXBREAK |  | 55.00 gal |  | 448.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
QMAXTHIN |  | 55.00 gal |  | 172.645 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
MAXBEADS |  | 50.00 lb |  | 29.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
GILSONITE AQUASOL 300 |  | 50.00 lb |  | 20.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
QMAXTROL |  | 25.00 kg |  | 100.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
HEC |  | 25.00 kg |  | 88.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
SODIUM CHLORIDE POWDER - BIG BAG |  | 1.00 Ton |  | 50.000 |  |  |  | 10.00 | 10.00 |  |  | 0.00 | 0 |  | 0.00 |  | 10.00
POTASSIUM CHLORIDE POWDER |  | 1.00 Ton |  | 175.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
QCIDE T |  | 5.00 gal |  | 18.000 |  |  |  | 16.00 | 16.00 |  |  | 0.00 | 0 |  | 0.00 |  | 16.00
QPAC HV |  | 25.00 kg |  | 33.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
QSCAV O2 |  | 25.00 kg |  | 32.000 |  |  |  |  | 0.00 |  |  | 0.00 | 0 |  | 0.00
Volume Accounting Summary
Volume Additions (bbl) | [9 empty] | Volume Transfers (bbl)
|  |  | Daily |  | Interval |  |  | Well | [7 empty] | Daily |  |  | Interval |  | Well
Whole Mud |  |  | 0.00 |  | 0.00 |  |  | 0.00 |  | Transfers from Active System | [5 empty] | 1100.00 |  |  | 1100.00 |  | 1100.00
Oil |  |  | 0.00 |  | 0.00 |  |  | 0.00 |  | Return to Warehouse/Rig/Other | [8 empty] | 0.00 |  | 0.00
Water |  |  | 1411.29 |  | 1411.29 |  |  | 1411.29 |  | Volume Losses (bbl)
Products |  |  | 32.29 |  | 32.29 |  |  | 32.29 | [7 empty] | Daily |  |  | Interval |  | Well
Weight Material |  |  | 56.42 |  | 56.42 |  |  | 56.42 |  | Surface Losses | [5 empty] | 15.00 |  |  | 15.00 |  | 15.00
Transferred from Reserve System |  |  | 0.00 |  | 0.00 |  |  | 0.00 |  | Subsurface Losses | [5 empty] | 0.00 |  |  | 0.00 |  | 0.00
Total Volume Additions |  |  | 1500.00 |  | 1500.00 |  |  | 1500.00 |  | Total Volume Losses | [5 empty] | 15.00 |  |  | 15.00 |  | 15.00
Services | [7 empty] | Pit Information | [10 empty] | Time Breakdown
Description |  |  | Qty. | Cum. |  | Cost (Kwd) |  | Active | [10 empty] | Rig-up / Service |  |  | 3.00
0 |  |  | 0 | 0 |  | 0 |  | Pit |  |  |  | Vol (bbl) | Density |  | Fluid Type |  |  |  | Circulating |  |  | 15.00
0 |  |  | 0 | 0 |  | 0 |  | Sand trap |  |  |  | 130.00 | 9.50 |  | GEL MUD |  |  |  | Pick Up BHA |  |  | 5.00
0 |  |  | 0 | 0 |  | 0 |  | Desander 1A | [10 empty] | Drilling Formation |  |  | 1.00
0 |  |  | 0 | 0 |  | 0 |  | Desilter 1B
0 |  |  | 0 | 0 |  | 0 |  | Intermidiate 2A |  |  |  | 98.00 | 9.50 |  | GEL MUD
0 |  |  | 0 | 0 |  | 0 |  | Intermediate 2B |  |  |  | 95.76 | 9.50 |  | GEL MUD
0 |  |  | 0 | 0 |  | 0 |  | Intermedate 2 C
0 |  |  | 0 | 0 |  | 0 |  | Trip Tank
0 |  |  | 0 | 0 |  | 0
Engineering
Description |  |  | Qty. | Cum. |  | Cost (Kwd)
Mud Supervisor-1 |  |  | 3.00 | 3.00 |  | 520.002
Mud Supervisor-2 |  |  |  | 0.00
Mud Supervisor-4 |  |  |  | 0.00 |  |  |  | Reserve
Mud Supervisor (Expatriate) |  |  |  | 0.00 |  |  |  | Pit |  |  |  | Vol (bbl) | Density |  | Fluid Type
Mud Supervisor (Expatriate)-2 |  |  |  | 0.00
Cost Summary
Cost Category |  |  | Kwd | [15 empty] | Cuttings Analysis
Daily Product Cost |  |  | 3135.700 | [5 empty] | 0 |  | 0 | [7 empty] | Depth Drilled Last 24 hrs (ft) |  |  | 96.0
Section Product Cost |  |  | 3135.700 |  |  |  |  | Suction 4A | 0 |  | 0 | 250.00 | 9.50 |  | Water-based |  |  |  | Vol. Drilled Last 24 hrs (bbl) |  |  | 45.14
Daily Eng. Cost |  |  | 520.002 |  |  |  |  | Suction 4B | 0 |  | 0 | 250.00 | 9.50 |  | Water-based |  |  |  | Interval Cum. Cuttings (bbl) |  |  | 45.14
Section Eng. Cost |  |  | 520.002 |  |  |  |  | Reserve 5A |  |  |  | 250.00 | 9.50 |  | Water-based |  |  |  | Well Cum. Cuttings (bbl) |  |  | 45.14
Cum. Product Cost |  |  | 3135.700 |  |  |  |  | Reserve 5B |  |  |  | 250.00 | 9.50 |  | Water-based
Cum. Eng. Cost |  |  | 520.002 |  |  |  |  | Reserve 6A |  |  |  | 100.00 | 9.50 |  | Water-based
Total Daily Cost |  |  | 3655.702 |  |  |  |  | Reserve 6B
Total Well Cost |  |  | 3655.702 |  |  |  |  | Pill 3A | 0 |  | 0
This report and the information contained therein is provided without any guarantee or warranty of any kind, either express or implied, including, but not limited to, warranties of merchantability, fitness for a particular purpose, of title, or of infringement of third party rights. Use of the information provided in this report is at the user’s risk.

## Info (hidden)
Version | 1.4
Description | Daily Mud Report for US Operations for Oil Base Drilling Fluids

## Version History (hidden)
Version | Changes
1.1 | - Added a volume balance with the detail of all the additions, the transfers and the losses as requested by Mike McKee - Moved the volume summary from the top to the bottom, next to the volume balance in order to compare side by side as requested by Mike McKee - New information in the “Volume Summary table like: “Daily Reserve Vol Built” and “Daily Reserve Vol Lost” - Added more information in the Rheology / Hydraulics table like: “Downhole Tools Pr Loss” and the “Motor Pr Loss” as requested by Mike McKee - Changed the product usage list to show only the products consumed during the day plus the daily cost, as requested by Mike McKee - Add a new Inventory page with the total inventory of the day and the cumulative for the well. This page is to be printed in the back of the report, as discussed with Mike McKee - Added the Oil density and the LGS density in the Solids Analysis Table as requested by Mike McKee
1.2 | - Added the taxes to the cost - Changed the color from green to blue (Anchor) - Added new drilling parameters and and more hydraulics results - Added a section for the hydraulics results by section - Added the product concentration in the 2nd page of the report - Added the Solids Analysis results for each fluid check - Compatible with version 1.8
1.3 | - Compatible with version 1.9 - Added Project ID in the header of the report
1.4 | - Compatible with version 2.0